## Proj. Gantt (Progress)
| Phase 1 - Blood Donation App | 2025-04-03 | [10 empty] | SA | S | M | T | W | TH | F | SA | S | M | T | W | TH | F | SA | S | M | T | W | TH | F | SA | S | M | T | W | TH | F | SA | S | M | T | W | TH | F | SA | S | M | T | W | TH | F | SA | S | M | T | W | TH | F | SA | S | M | T | W | TH | F | SA | S | M | T | W | TH | F | SA | S | M | T | W | TH | F
ID | Task Name | Planned Start | Dur. | Planned Finish | P % | A % | Start | Dur. | Finish | Delay | Status | Responsible | [288 empty] | Remarks | time axis 2021-03-01 to 2021-12-24
| Project Planning & Initial Setup | 2025-03-10 | 19 | 2025-04-04 | 96%
1 | Initial Setup - API Endpoint | 2025-03-10 | 5 | 2025-03-14 | 100% | [5 empty] | None | Programmer | bar: 2021-03-10 to 2021-03-14
2 | Initial Setup - UI, Users, Roles & Roles | 2025-03-17 | 5 | 2025-03-21 | 100% | [5 empty] | None | Programmer | bar: 2021-03-17 to 2021-03-21
3 | Data Gathering, Define Project Scope and requirements | 2025-03-24 | 3 | 2025-03-26 | 100% | [5 empty] | None | Project Analyst, Programmer | bar: 2021-03-24 to 2021-03-26
4 | Database schema Design | 2025-03-27 | 2 | 2025-03-28 | 100% | [5 empty] | None | Programmer | bar: 2021-03-27 to 2021-03-28
5 | Wireframing | 2025-03-31 | 4 | 2025-04-04 | 75% | [5 empty] | None | Programmer | bar: 2021-03-31; 2021-04-02 to 2021-04-04
| Admin Panel & Access Management | 2025-04-07 | 5 | 2025-04-11 | 0%
6 | Access Management (RBAC) | 2025-04-07 | 2 | 2025-04-08 | 0% | [5 empty] | None | Programmer
7 | Admin - Blood Drive Hosting ( Approval of Request ) | 2025-04-09 | 1 | 2025-04-09 | 0% | [5 empty] | None | Programmer
8 | Authentication (App Login / Forgot Password / Email Validation) | 2025-04-10 | 2 | 2025-04-11 | 0% | [5 empty] | None | Programmer
| Blood Drive Hosting (Agency) | 2025-04-14 | 15 | 2025-04-21 | 0%
6 | Blood Drive Hosting Request (Registration) | 2025-04-14 | 1 | 2025-04-14 | 0% | [5 empty] | None | Programmer
7 | Profile Management - (View & Update Profile) | 2025-04-15 | 1 | 2025-04-15 | 0% | [5 empty] | None | Programmer
8 | Manage Coordinators ( List / Approval Request / Activate / Deactivate ) | 2025-04-16 | 1 | 2025-04-16 | 0% | [5 empty] | None | Programmer
9 | Manage Donors ( List / Activate / Deactivate ) | 2025-04-17 | 1 | 2025-04-17 | 0% | [5 empty] | None | Programmer
10 | Dashboard | 2025-04-18 | 1 | 2025-04-18 | 0% | [5 empty] | None | Programmer
| Blood Drive Hosting (Coordinators) | 2025-04-19 | 5 | 2025-04-21 | 0%
11 | Blood Program Leader Access Request | 2025-04-21 | 1 | 2025-04-21 | 0% | [5 empty] | None | Programmer
12 | Profile Management - (View & Update Profile) | 2025-04-22 | 1 | 2025-04-20 | 0% | [5 empty] | None | Programmer
13 | Donor Authentication (App Login / Forgot Password / Email Validation) | 2025-04-21 | 1 | 2025-04-19 | 0% | [5 empty] | None | Programmer
14 | Donor Authentication (App Login / Forgot Password / Email Validation) | 2025-04-20 | 1 | 2025-04-18 | 0% | [5 empty] | None | Programmer
15 | Donor Authentication (App Login / Forgot Password / Email Validation) | 2025-04-19 | 1 | 2025-04-18 | 0% | [5 empty] | None | Programmer
| Donor Registration & Authentication | 2025-04-21 | 5 | 2025-04-25 | 0%
16 | Donor Registration (Register / Update Profile) | 2025-04-21 | 2 | 2025-04-22 | 0% | [5 empty] | None | Programmer
17 | Donor Authentication (App Login / Forgot Password / Email Validation) | 2025-04-23 | 3 | 2025-04-25 | 0% | [5 empty] | None | Programmer
| Blood Donation Drive Management - Organizers | 2025-04-28 | 10 | 2025-05-12 | 0%
18 | Admin Management | 2025-04-28 | 5 | 2025-05-05 | 0% | [5 empty] | None | Programmer
19 | Donor Pre-Registration | 2025-05-06 | 5 | 2025-05-12 | 0% | [5 empty] | None | Programmer
| Content Management System | 2025-05-13 | 5 | 2025-05-19 | 0%
20 | Education & FAQ's | 2025-05-13 | 5 | 2025-05-19 | 0% | [5 empty] | None | Programmer
| QA and Testing | 2025-05-20 | 5 | 2025-05-26 | 0%
21 | Education & FAQ's | 2025-05-20 | 5 | 2025-05-26 | 0% | [5 empty] | None | Project Analyst, Programmer
| User Acceptance Test (UAT) | 2025-05-27 | 5 | 2025-06-02 | 0%
22 | UAT (MBD Team) | 2025-05-27 | 5 | 2025-06-02 | 0% | [5 empty] | None | MBD Team, End-user
| Revisions (if any) | 2025-06-03 | 1 | 2025-06-03 | 0%
23 | TBD | 2025-06-03 | 1 | 2025-06-03 | 0% | [5 empty] | None | Programmer
| Deployment | 2025-06-04 | 6 | 2025-06-10 | 0%
24 | Production Environment Deployment/Testing | 2025-06-04 | 5 | 2025-06-10 | 0% | [5 empty] | None | Programmer
25 | Product Demo & Acceptance | 2025-06-11 | 1 | 2025-06-11 | 0% | [5 empty] | None | Project Analyst, Programmer, End-User
| TAT (in months) |  | 3.05
Legend:
On Track
Done (Completed)
Done (For Approval)
Delayed
Critical
On-Hold
Adjusted
Planned Start/Finish

## Ref
Status
None
On Track
Done (Completed)
Done (For Approval)
Delayed
Critical
On-Hold
Adjusted