## Website
Requirements Traceability Matrix
Project | Website
As of | 2025-04-08
Responsible | Erwin Guinto
Requirement # | Description | Sprint Reference | Date Start | Date Completed | Priority | Test Case Reference | Date Start | Date Completed | Status | Responsible | User Acceptance Validation | Remarks
1 | Add link for ICTD help desk |  | 2024-02-26 | 2024-02-26 | Urgent |  |  |  | Closed
2 | Add Page for linkbiz portal |  | 2024-03-04 | 2024-03-04 |  |  |  |  | Closed
3 | New layout of homepage bank partners and landing page for landbank linkbiz portal |  | 2024-03-05 | 2024-03-05 |  |  |  |  | Closed

## CMS
Requirements Traceability Matrix
Project | Case Management System
As of | 2025-04-08
Responsible | RJ Cabarong & Joel Manaloto
Requirement # | Description | Responsible | Sprint Reference | Date Start | Date Completed | Priority | Test Case Reference | Date Start | Date Completed | Status | Requestor | User Acceptance Validation | Remarks
1 | Items under Nature of the case dropdown | Rj | Sprint 1 |  | 2023-07-24 | Important |  |  |  | Closed | Atty. Kat/Atty. Mitch | None
2 | PDF format of Summons with TRO and Summons without TRO | Rj | Sprint 1 |  | 2023-08-16 | Important |  |  |  | Closed | Atty. Kat/Atty. Mitch | None
3 | Items under Unsuccessful (Service of Summons) dropdown | Rj | Sprint 1 |  | 2023-07-24 | Important |  |  |  | Closed | Atty. Kat/Atty. Mitch | None
4 | User - Add | Rj | Sprint 2 |  | 2023-07-08 | Important | Sprint 5-Retro Meeting | 2023-07-08 | 2023-07-08 | Closed | ICTD | None
5 | User - Edit | Rj | Sprint 2 |  | 2023-07-08 | Important | Sprint 5-Retro Meeting | 2023-07-08 | 2023-07-08 | Closed | ICTD | None
6 | User - Delete | Rj | Sprint 2 |  | 2023-07-08 | Important | Sprint 5-Retro Meeting | 2023-07-08 | 2023-07-08 | Closed | ICTD | None
7 | Permission - Add | Rj | Sprint 2 |  | 2023-07-08 | Important | Sprint 5-Retro Meeting | 2023-07-08 | 2023-07-08 | Closed | ICTD | None
8 | Permission - Edit | Rj | Sprint 2 |  | 2023-07-08 | Important | Sprint 5-Retro Meeting | 2023-07-08 | 2023-07-08 | Closed | ICTD | None
9 | Permission - Delete | Rj | Sprint 2 |  | 2023-07-08 | Important | Sprint 5-Retro Meeting | 2023-07-08 | 2023-07-08 | Closed | ICTD | None
10 | Case - Add upload multiple files | Rj | Sprint 3 |  | 2023-07-08 | Important | Sprint 5-Retro Meeting | 2023-07-08 | 2023-07-08 | Closed | ICTD | None
11 | Settings - Branch | Rj | Sprint 3 |  | 2023-07-08 | Important | Sprint 5-Retro Meeting | 2023-07-08 | 2023-07-08 | Closed | ICTD | None
12 | Settings - Nature of Case | Rj | Sprint 3 |  | 2023-07-08 | Important | Sprint 5-Retro Meeting | 2023-07-08 | 2023-07-08 | Closed | ICTD | None | Waiting for RABs (Nature of Case data)
13 | Settings - Remove Adjudicator | Rj | Sprint 4 |  | 2023-07-08 | Important | Sprint 5-Retro Meeting | 2023-07-08 | 2023-07-08 | Closed | ICTD | None
14 | Superadmin - Add feature to reset password thru email | Rj | Sprint 4 |  | 2023-08-22 | Important |  |  |  | None | ICTD | None
15 | Case - Add Regular Case tab | Rj | Sprint 4 |  | 2023-07-08 | Important | Sprint 5-Retro Meeting | 2023-07-08 | 2023-07-08 | Closed | ICTD | None
16 | Case - Add with TRO Case tab | Rj | Sprint 4 |  | 2023-07-08 | Important | Sprint 5-Retro Meeting | 2023-07-08 | 2023-07-08 | Closed | ICTD | None
17 | Nature of Case Dropdown format | Rj | Sprint 4 |  | 2023-08-31 | Important |  |  |  | None | ICTD | None
18 | New items under Nature of the Case dropdown | Rj | Sprint 4 |  | 2023-08-31 | Important |  |  |  | None | Atty. Kat/Atty. Mitch | None
19 | Case - upload files - save filename only, do not upload the file | Rj | Sprint 4 |  | 2023-07-08 | Important | Sprint 5-Retro Meeting | 2023-07-08 |  | None | ICTD | None | Can still upload files
20 | Case - Listings - add name of the assigned adjudicator | Rj | Sprint 4 |  | 2023-07-08 | Important | Sprint 5-Retro Meeting | 2023-07-08 |  | None | ICTD | None
21 | Case - Add new tab (Summons) | Rj | Sprint 4 |  | 2023-07-08 | Important | Sprint 5-Retro Meeting | 2023-07-08 |  | None | ICTD | None
22 | Case - Download PDF of Case Details | Rj | Sprint 5 |  |  | Important |  |  |  | None | ICTD | None
23 | Case - Hide case status dropdown | Rj | Sprint 5 |  | 2023-07-08 | Important | Sprint 5-Retro Meeting | 2023-07-08 |  | None | ICTD | None
24 | Case - for raffling - no adjudicator | Rj | Sprint 5 |  | 2023-07-08 | Important | Sprint 5-Retro Meeting | 2023-07-08 |  | None | ICTD | None
25 | Case - for summons - raffled | Rj | Sprint 5 |  | 2023-07-08 | Important | Sprint 5-Retro Meeting | 2023-07-08 |  | None | ICTD | None
26 | User - Permission - Access Control | Rj | Sprint 5 |  | 2023-07-08 | Important |  |  |  | None | Atty. Kat/Atty. Mitch | None
27 | Notifications - with tro tab - notify user before the cutoff (3pm) the same day after the filing date | Rj | Sprint 5 |  | 2023-08-17 | Important |  |  |  | None | ICTD | None
28 | Notifications - regular cases - notify user 8 days after the filing date | Rj | Sprint 5 |  | 2023-08-17 | Important |  |  |  | None | ICTD | None
29 | Case - Edit Case - Can reupload /delete files | Rj | Sprint 5 |  | 2023-08-08 | Important |  |  |  | None | ICTD | None
30 | Case - View Case - All Users can view case | Rj | Sprint 5 |  | 2023-08-08 | Important |  |  |  | None | ICTD | None
30 | Case - Add Case - Add sample case files | Rj | Sprint 5 |  | 2023-08-08 | Important |  |  |  | None | ICTD | None
31 | Role - Change Adjudicator to Regional Adjudicator | Rj | Sprint 5 |  | 2023-08-08 | Important |  |  |  | None | ICTD | None
32 | Case - Summons - Clarify how many templates for summons | Rj | Sprint 5 |  | 2023-08-15 | Important |  |  |  | None |  | None
33 | Case - Summons - Clarify the date on the letter for summons (Current date) | Rj | Sprint 5 |  | 2023-08-10 | Important |  |  |  | None | ICTD | None
34 | Settings - Add on Branch the Address of the RABs. (Connect to Summons Template) | Rj | Sprint 5 |  | 2023-08-10 | Important |  |  |  | None | ICTD | None
35 | Case - Summons - Before viewing of pdf, the case status must be Awaiting Summons | Rj | Sprint 5 |  | 2023-08-16 | Important |  |  |  | None | ICTD | None
36 | Case - Notifications - Bell icon | Rj | Sprint 5 |  | 2023-08-16 | Important |  |  |  | None | ICTD | None
37 | Case - Notifications - Message box - For TRO, if 1 day has passed and it is not yet raffled, display message box (in general) | Rj | Sprint 5 |  | 2023-08-17 | Important |  |  |  | None | ICTD | None
37 | Case - Notifications - Message box - For Regular Cases, if 8 days has passed and it is not yet raffled, display message box (in general) | Rj | Sprint 5 |  | 2023-08-17 | Important |  |  |  | None | ICTD | None
38 | Case - Tables - On Actions, User can view, edit and issue summons depending on the branch that the user belongs | Rj | Sprint 5 |  | 2023-08-17 | Important |  |  |  | None | ICTD | None
39 | Case - Tables - On Actions, if the case status is Awaiting Summons, the user can still view the summons file. | Rj | Sprint 5 |  | 2023-08-17 | Important |  |  |  | None | ICTD | None
40 | Case - Summons - The pdf file should have a footer with page number on every page. | Rj | Sprint 5 |  | 2023-08-18 | Important |  |  |  | None | ICTD | None
41 | Users - Add the Roles and their corresponding permissions for testing. | Rj | Sprint 5 |  | 2023-08-22 | Important |  |  |  | None | ICTD | None
42 | Users - Remove notifications and message box for "Normal User" role. | Rj | Sprint 6 |  | 2023-08-23 | Important |  |  |  | None | ICTD | None
43 | Users - Remove notifications and message box for "Receiving Officer" role. | Rj | Sprint 6 |  | 2023-08-23 | Important |  |  |  | None | ICTD | None
44 | Users - Add "Raffling Officer" role that can only view case and assign adjudicator. | Rj | Sprint 6 |  | 2023-08-23 | Important |  |  |  | None | ICTD | None
45 | Case - Edit Case - Only the assigned adjudicator (if already raffled), their legal assistant, Super Admin and Legal Administrator can edit case details. | Rj | Sprint 6 |  | 2023-08-31 | Important |  |  |  | None | ICTD | None
44 | Case - Edit Case - Case title should be updated/edited by the assigned adjudicator, their legal assistant, Super Admin and Legal Administrator. | Rj | Sprint 6 |  | 2023-09-05 | Important |  |  |  | None | ICTD | None
45 | Issue Summons - Sample format of the FINAL summons template. | Rj | Sprint 6 |  | 2023-12-06 | Important |  |  |  | None | Atty. Mitch | None
46 | Issue Summons - Add also the "Complainants" on "TO:" in Summons file. | Rj | Sprint 6 |  | 2023-08-24 | Important |  |  |  | None | ICTD | None
47 | Issue Summons - The first page has no footer. | Rj | Sprint 6 | ` | 2023-08-24 | Important |  |  |  | None | ICTD | None
48 | Issue Summons - On the second page onwards, the current footer will be the header. | Rj | Sprint 6 |  | 2023-08-24 | Important |  |  |  | None | ICTD | None
49 | Case - Status - Change the status name of "Awaiting Summons" to "Awaiting Service of Summons". | Rj | Sprint 6 |  | 2023-08-23 | Important |  |  |  | None | ICTD | None
50 | Case - Status - Add "Awaiting Answer" and "Awaiting Proof of Service" statuses. | Rj | Sprint 6 |  | 2023-09-05 | Important |  |  |  | None | ICTD | None
51 | Case - Notifications - If the respondent don't have an answer yet, it will appear on the notifications 3 days before the 20-day countdown from the date of delivery. After uploading an answer, it will disappear on the notifications. | Rj | Sprint 6 |  | 2023-09-05 | Important |  |  |  | None | ICTD | None
52 | Case - Actions - Add Upload "Proof of Service". Add fields on the form for complainants/respondents names and date of delivery for each of them. | Rj | Sprint 6 |  | 2023-09-05 | Important |  |  |  | None | ICTD | None
53 | Case - Actions - Add Upload "Answer". Add fields on the form for complainants/respondents names and date of delivery for each of them. | Rj | Sprint 6 |  | 2023-09-05 | Important |  |  |  | None | ICTD | None
54 | Users - Attach a Legal Assistant if the role of the user is Regional Adjudicator. | Rj | Sprint 6 |  | 2023-08-24 | Important |  |  |  | None | ICTD | None
55 | Case - Status - Change the "Awaiting Service of Summons" to "Awaiting Proof of Service". | Rj | Sprint 7 |  | 2023-09-07 | Important |  |  |  | None | ICTD | None
56 | Case - Status - Once all the Proof of Service for Respondents are uploaded, the case status will change to "Awaiting Answer". | Rj | Sprint 7 |  | 2023-09-20 | Important |  |  |  | None | ICTD | None
57 | Case - Status - Once all the Answer of Respondents are uploaded, the case status will change to "For Mandatory Conference". | Rj | Sprint 7 |  | 2023-09-20 | Important |  |  |  | None | ICTD | None
58 | Case - Actions - Add "Mediation" only if the case status is already "For Mandatory Conference". | Rj | Sprint 7 |  | 2023-09-20 | Important |  |  |  | None | ICTD | None
59 | Case - Actions - Create the "Mediation" form with inputs to change the case status and upload files. | Rj | Sprint 7 |  | 2023-09-20 | Important |  |  |  | None | ICTD | None
60 | Case - Actions - Add "Assign Mediator" only for Raffling Officer. | Rj | Sprint 7 |  | 2023-09-20 | Important |  |  |  | None | ICTD | None
60 | Case - Actions - Create the form for assigning mediator for the case. Mediator can be anyone in the RAB except for adjudicator, their legal assistant. chief regional adjudicator and raffling officer. Add a "mediator_id" for the cases table on database. | Rj | Sprint 7 |  | 2023-09-20 | Important |  |  |  | None | ICTD | None
61 | Case - Mediation - Add "For PP/DD" case status and upload Minutes, Order and Proof of Service on the mediation form after the status "For Reporting" with a sub-status of "Settled" or "Failed to settle". | Rj | Sprint 8 |  | 2023-10-27 | Important |  |  |  | None | ICTD | None
62 | Case - Actions - For Raffling Officer, if the case status is "For Raffling", the actions should be View and Assign Adjudicator. | Rj | Sprint 8 |  | 2023-10-27 | Important |  |  |  | None | ICTD | None
63 | Case - Actions - For Raffling Officer, if the case status is "For Mediation", the actions should be View and Assign Mediator. | Rj | Sprint 8 |  | 2023-10-27 | Important |  |  |  | None | ICTD | None
64 | Case - Actions - For Raffling Officer, for other case statuses, the action should only be "View". | Rj | Sprint 8 |  | 2023-10-27 | Important |  |  |  | None | ICTD | None
65 | Case - Actions - For Regional Adjudicator/Legal Assistant, if the case status is "For Mediation", remove the "Mediation" on its actions menu. | Rj | Sprint 8 |  | 2023-10-27 | Important |  |  |  | None | ICTD | None
66 | Case - Tables - Make the tables mobile responsive. | Rj | Sprint 8 |  | 2023-10-27 | Important |  |  |  | None | ICTD | None
67 | Case - Tables - Fix the selection tab of the data table for "mobile screens". | Rj | Sprint 8 |  | 2023-10-27 | Important |  |  |  | None | ICTD | None
68 | Case - Tables - Make the case number to be a link to View Case Details. | Rj | Sprint 8 |  | 2023-10-27 | Important |  |  |  | None | ICTD | None
69 | Case - View - Make the case status in the view case page to be color coded. | Rj | Sprint 8 |  | 2023-10-27 | Important |  |  |  | None | ICTD | None
70 | Audit logs - Add triggers for Insert, Update and Delete on tables of cases, admins, mediation and uploaded_files. | Rj | Sprint 8 |  | 2023-10-27 | Important |  |  |  | None | ICTD | None
71 | Audit logs - Create the tables for the audit logs. | Rj | Sprint 8 |  | 2023-10-27 | Important |  |  |  | None | ICTD | None
72 | Audit logs - Display the logs to be accessed only by the Super Admin and Legal Admin. | Rj | Sprint 8 |  | 2023-10-27 | Important |  |  |  | None | ICTD | None
73 | Case - Summons - Addressee Left side for Complainants, Right Side for Respondents | Rj | Sprint 9 |  | 2023-10-27 | Important |  |  |  | None | ICTD | None
74 | Case - Summons - If litigant has a lawyer, change addressee to lawyer | Rj | Sprint 9 |  | 2023-10-27 | Important |  |  |  | None | ICTD | None
75 | Case - Summons - For page 2 onwards place "Page _ of _" | Rj | Sprint 9 |  | 2023-10-27 | Important |  |  |  | None | ICTD | None
76 | Case - Actions - Order of Dismissal process. | Rj | Sprint 10 |  | 2023-11-10 | Important |  |  |  | None | ICTD | None
77 | Case - Actions - Order of Payment process. | Rj | Sprint 10 |  | 2023-11-10 | Important |  |  |  | None | ICTD | None
78 | Case - Actions - Order to Implead process. | Rj | Sprint 10 |  | 2023-11-10 | Important |  |  |  | None | ICTD | None
79 | Case - Actions - Order of Inhibition process. | Rj | Sprint 10 |  | 2023-11-10 | Important |  |  |  | None | ICTD | None
80 | Case - Notifications - Incomplete Proof of Service for the Orders. | Rj | Sprint 10 |  | 2023-11-10 | Important |  |  |  | None | ICTD | None
81 | Case - Summons - Revision | Rj | Sprint 11 |  | 2023-11-22 | Important |  |  |  | None | ICTD | None
82 | Case - Add Case - Revision for Adding Complainants/Respondents and their corresponding Representatives and Counsels. (Frontend, Backend) | Rj | Sprint 11 |  | 2023-12-05 | Important |  |  |  | None | ICTD | None
83 | Case - Edit Case - Revision for Updating/Adding of Complainants/Respondents and their corresponding Representatives and Counsels. (Frontend, Backend) | Rj | Sprint 11 |  | 2023-12-07 | Important |  |  |  | None | ICTD | None
84 | Case - View - Revision to display the Complainants/Respondents and their corresponding Representatives and Counsels. (Frontend, Backend) | Rj | Sprint 11 |  | 2023-12-08 | Important |  |  |  | None | ICTD | None
85 | Case - Summons - Upload Summon Signed page. | Rj | Sprint 11 |  | 2023-12-08 | Important |  |  |  | None | ICTD | None
86 | Case - Summons - Upload POS - Summons for Respondents page. | Rj | Sprint 11 |  | 2023-12-08 | Important |  |  |  | None | ICTD | None
87 | Case - Summons - Upload Answer for Respondents and Other Pleadings for Complainants page. | Rj | Sprint 12 |  | 2023-12-15 | Important |  |  |  | None | ICTD | None
88 | Case - Summons - Add Contact Details on each Complainant/Respondent and their corresponding Representative/s and Counsel/s on Answer/Other pleadings page. | Rj | Sprint 12 |  | 2023-12-15 | Important |  |  |  | None | ICTD | None
89 | Case - Edit - Add Contact Details on each Complainant/Respondent and their corresponding Representative/s and Counsel/s. | Rj | Sprint 12 |  | 2023-12-15 | Important |  |  |  | None | ICTD | None
90 | Case - Status - Auto-change of the case status. | Rj | Sprint 12 |  | 2024-04-05 | Important |  |  |  | None | ICTD | None
91 | Case - Notifications - Proof of Service - Summons. | Rj | Sprint 12 |  | 2024-04-05 | Important |  |  |  | None | ICTD | None
92 | Case - Actions - Motion for Default process | Rj | Sprint 13 |  | 2024-01-29 | Important |  |  |  | None | ICTD | None
93 | Case - Actions - Order of Default process | Rj | Sprint 13 |  | 2024-01-30 | Important |  |  |  | None | ICTD | None
94 | Case - Actions - Resolution - Default process | Rj | Sprint 14 |  | 2024-01-31 | Important |  |  |  | None | ICTD | None
95 | Case - Mandatory Conference - Generate Notice | Rj | Sprint 15 |  | 2024-02-13 | Important |  |  |  | None | ICTD | None
96 | Case - Actions - Order for Position Paper | Rj | Sprint 15 |  | 2024-03-26
97 | Add New Case - Has Representative? Include Upload SPA/Sec Cert (both Complainant and Respondent) | Rj | Sprint 15 |  | 2024-02-23 | Important
98 | Admin - Add Nature of Case - Complete all abbreviations/acronyms | Rj | Sprint 15 |  | 2024-02-15 | Important
99 | Add New Case - Filter if complainant and respondent are interchange or similar (Flag legal admin and CRA via email or notifications or prompt) | Rj | Sprint 15 |  |  | Important
100 | Issue summons - Remove Date of Issuance | Rj | Sprint 15 |  | 2024-02-23 | Important
101 | PPDD - add another entity (Date Received) | Rj | Sprint 15 |  | 2024-04-05 | Important | Ask Johnry for further details
102 | General - for all et. al. change it to et al. | Rj | Sprint 15 |  | 2024-02-15 | Important
103 | General - Put * for all required entities for Add/Edit Case Form | Rj | Sprint 15 |  | 2024-02-22 | Important
104 | Mandatory and mediation (Video Conference) include NDA | Rj | Sprint 15 |  |  | Important | To be discussed with legal
105 | Monitoring/Reporting dashboard (Aging of cases) | Rj | En Banc |  |  | Important
106 | Mandatory Conference default is face-to-face | Rj | En Banc |  |  | Important | Ask Johnry for further details
107 | Case - Edit - Implement "is_active" status on the Complainants/Respondents | Rj | Sprint 16 |  | 2024-03-15 | Important
108 | Settings - Case Proceedings | Rj | Sprint 16 |  | 2024-03-15 | Important
109 | Case Proceedings - Add/Remove proceedings on a case | Rj | Sprint 16 |  | 2024-03-15 | Important
110 | Case - Proceeding - Redo the code for regular proceeding | Rj | Sprint 17 |  | 2024-03-22 | Important
111 | Case - Order for Position Paper process | Rj | Sprint 18 |  | 2024-03-26 | Important
112 | Case - Notice of Decision/Decision process | Rj | Sprint 18 |  | 2024-04-05 | Important
113 | Add New Case - Upload required documents | Rj | Sprint 18 |  | 2024-04-05 | Important
114 | Edit Case - Update/Edit uploaded required documents | Rj | Sprint 18 |  | 2024-04-12 | Important
115 | Case - NOD/Decision - POS of NOD and Decision are the same. | Rj | Sprint 19 |  | 2024-04-12 | Important
116 | Case - Appeal Memorandum process | Rj | Sprint 19 |  | 2024-04-17 | Important
117 | Case - Appeal Memorandum - Add upload annexes for the appeal. | Rj | Sprint 19 |  | 2024-04-17 | Important
118 | Case - Answer - Add upload annexes for the answer | Rj | Sprint 19 |  | 2024-04-24 | Important
119 | Case - Order of Finality process | Rj | Sprint 19 |  | 2024-04-19 | Important
120 | Case - Order to Elevate process | Rj | Sprint 19 |  | 2024-04-19 | Important
121 | Case - Notice of Receipt of Records process | Rj | Sprint 19 |  | 2024-04-19 | Important
122 | Case - Certificate of Finality process | Rj | Sprint 19 |  | 2024-04-19 | Important
123 | Case - Mandatory Conference - Make the Signed Notice for Mandatory Conference to be multiple and add date issued for each file that was uploaded. (This is because "resetting" the case will require a new Notice for Mandatory Conference.) | Rj | Sprint 20 |  |  | Important
124 | Case - Mandatory Conference - Minutes for MC | Rj | Sprint 20 |  |  | Important
125 | Case - Mandatory Conference - Revise the Proof of Service of Notice for Mandatory Conference frontend and backend. (Affected because of the Requirement #123) | Rj | Sprint 20 |  |  | Important
126 | Case - Notifications - Code revision for Proof of Service of Notice for Mandatory Conference's notification. (Affected because of the Requirement #125) | Rj | Sprint 20 |  |  | Important
127 | Case - Documents - Add a feature that reuploading/changing/removing the file only lasts for 5 days from the uploading date. | Rj | Sprint 20 |  |  | Important
128 | Case - Minutes for MC - Settled process | Rj | Sprint 20 |  |  | Important
129 | Case - Minutes for MC - Resetting process | Rj | Sprint 20 |  |  | Important
130 | Case - Minutes for MC - Mediation process | Rj | Sprint 20 |  |  | Important
131 | Case - Minutes for MC - Terminated process | Rj | Sprint 20 |  |  | Important
132 | Notification- Include the due date (Automatically computes the due date) | Rj | Legal Forum Demo | 2024-05-22 |  | Important
133 | View - Restrict to Viewing (For Discussion) | Rj | Legal Forum Demo | 2024-05-22 |  | Important
134 | View - Restrict to Viewing (For Discussion) | Rj | Legal Forum Demo | 2024-05-22 |  | Important
135 | Cloning the current CMS to a latest Laravel and PHP version. (Ongoing) | Rj | Remake CMS | 2024-06-03 |  | Important
136 | Users - Login | Rj | Sprint 21 | 2024-06-03 | 2024-06-05 | Important
137 | Users - Multiple Role and Permissions | Rj | Sprint 21 | 2024-06-03 | 2024-06-06 | Important
138 | Settings - Branches | Rj | Sprint 21 | 2024-06-03 | 2024-06-10 | Important
139 | Settings - Case Types | Rj | Sprint 21 | 2024-06-03 | 2024-06-11 | Important
140 | Settings - Nature of Cases | Rj | Sprint 21 | 2024-06-03 | 2024-06-12 | Important
141 | Settings - Proceedings | Rj | Sprint 21 | 2024-06-03 | 2024-06-13 | Important
142 | Settings - Statuses | Rj | Sprint 21 | 2024-06-03 | 2024-06-14 | Important
143 | Cases - Add and Edit Case | Rj | Sprint 21 | 2024-06-03 | 2024-06-18 | Important
144 | Cases - Regular Case Actions on the table | Rj | Sprint 21 | 2024-06-03 | 2024-06-19 | Important
145 | Cases - Add Proceedings to the Case | Rj | Sprint 21 | 2024-06-03 | 2024-06-21 | Important
146 | Cases - Raffle Adjudicator for the Case | Rj | Sprint 21 | 2024-06-03 | 2024-06-26 | Important
147 | Cases - Regular Case Proceeding - Generate Summons, upload Signed Summons, POS and Answer | Rj | Sprint 21 | 2024-06-03 | 2024-06-28 | Important
148 | Cases - Regular Case Proceeding - Generate Notice for MC, upload Signed Notice and POS | Rj | Sprint 22 | 2024-06-17 | 2024-06-28 | Important
149 | Cases - Regular Case Proceeding - Minutes for Mandatory Conference | Rj | Sprint 22 | 2024-06-17 | 2024-06-28 | Important
150 | Cases - Regular Case Proceeding - Mandatory Conference Result: Settled Process | Rj | Sprint 22 | 2024-06-17 | 2024-07-02 | Important
151 | Cases - Regular Case Proceeding - Mandatory Conference Result: For Resetting Process | Rj | Sprint 22 | 2024-06-17 | 2024-07-02 | Important
152 | Cases - Regular Case Proceeding - Mandatory Conference Result: For Mediation Process | Rj | Sprint 22 | 2024-06-17 | 2024-07-03 | Important
153 | Cases - Regular Case Proceeding - Mandatory Conference Result: Terminated Process | Rj | Sprint 22 | 2024-06-17 | 2024-07-03 | Important
154 | Cases - Regular Case Proceeding - Mediation: Raffle Mediator, Generate Notice for Mediation, upload Signed Notice and POS | Rj | Sprint 22 | 2024-06-17 | 2024-07-04 | Important
155 | Cases - Regular Case Proceeding - Report of Mediation: Settled process | Rj | Sprint 22 | 2024-06-17 | 2024-07-04 | Important
156 | Cases - Regular Case Proceeding - Report of Mediation: For Resetting process | Rj | Sprint 22 | 2024-06-17 | 2024-07-04 | Important
157 | Cases - Regular Case Proceeding - Report of Mediation: Terminated process | Rj | Sprint 22 | 2024-06-17 | 2024-07-05 | Important
158 | Cases - Regular Case Proceeding - Generate Order for Position Paper, upload Signed Order and POS | Rj | Sprint 22 | 2024-06-17 | 2024-07-05 | Important
159 | Cases - Regular Case Proceeding - Upload Position Paper | Rj | Sprint 22 | 2024-06-17 | 2024-07-05 | Important
160 | Cases - Regular Case Proceeding - Generate Order Ripe for Resolution and upload the signed order | Rj | Sprint 23 | 2024-07-01 | 2024-07-05 | Important
161 | Cases - Regular Case Proceeding - Generate Notice of Decision, upload signed notice, decision and POS | Rj | Sprint 23 | 2024-07-01 | 2024-07-09 | Important
162 | Cases - Regular Case Proceeding - Upload Appeal Memorandum and its required documents | Rj | Sprint 23 | 2024-07-01 | 2024-07-09 | Important
163 | Cases - Regular Case Proceeding - Generate Order to Elevate, upload the signed order | Rj | Sprint 23 | 2024-07-01 | 2024-07-10 | Important
164 | Cases - Regular Case Proceeding - Generate Order of Finality, upload the signed order, NRR, and Certificate of Finality | Rj | Sprint 23 | 2024-07-01 | 2024-07-10 | Important
165 | Cases - Regular Case Proceeding - Dismissal of the Case | Rj | Sprint 23 | 2024-07-01 | 2024-07-11 | Important
166 | Cases - Regular Case Proceeding - Other Orders: Order of Payment process | Rj | Sprint 23 | 2024-07-01 | 2024-07-11 | Important
167 | Cases - Regular Case Proceeding - Other Orders: Order to Implead process | Rj | Sprint 23 | 2024-07-01 | 2024-07-12 | Important
168 | Cases - Regular Case Proceeding - Other Orders: Order to Inhibit process | Rj | Sprint 23 | 2024-07-01 | 2024-07-12 | Important
169 | Cases - Regular Case Proceeding - Upload Motion for Approval of CA | Rj | Sprint 23 | 2024-07-01 | 2024-07-12 | Important
170 | Cases - Regular Case Proceeding - Order for Default and Motion for Default process | Rj | Sprint 23 | 2024-07-01 | 2024-07-12 | Important
171 | Dashboard - Stats Overview Widgets for Overall Cases | Rj | Sprint 24 | 2024-07-15 | 2024-07-15 | Medium
172 | Dashboard - Stats Overview Widgets for the Cases of user's RAB | Rj | Sprint 24 | 2024-07-15 | 2024-07-15 | Medium
173 | Dashboard - Chart Widgets about the monthly cases of overall and per branch | Rj | Sprint 24 | 2024-07-15 | 2024-07-16 | Medium
174 | Dashboard - Table Widget for the recently added cases | Rj | Sprint 24 | 2024-07-15 | 2024-07-16 | Medium
175 | Audit - Activity log for the Users | Rj | Sprint 24 | 2024-07-15 | 2024-07-17 | Important
176 | Audit - Activity log fot the Cases | Rj | Sprint 24 | 2024-07-15 | 2024-07-17 | Important
177 | Calendar Events - Add Events to the Calendar regarding the Mandatory Conference and Mediation | Rj | Sprint 24 | 2024-07-15 | 2024-07-18 | Medium
178 | Calendar Events - Show the Events on the Calendar, can be added after generating the Notice for MC or Mediation | Rj | Sprint 24 | 2024-07-15 | 2024-07-18 | Medium
179 | Calendar Events - Added events can be updated or deleted by Admins | Rj | Sprint 24 | 2024-07-15 | 2024-07-18 | Medium
180 | Email - Send email to the assigned adjudicator after raffling | Rj | Sprint 24 | 2024-07-15 | 2024-07-09 | Important
181 | Email - Send email to the adjudicator if they are replaced by another adjudicator | Rj | Sprint 24 | 2024-07-15 | 2024-07-09 | Important
182 | Email - Send email to the assigned mediator after raffling | Rj | Sprint 24 | 2024-07-15 | 2024-07-10 | Important
183 | Email - Send email to the mediator if they are replace by another mediator | Rj | Sprint 24 | 2024-07-15 | 2024-07-10 | Important
184 | Maintenance switch - Added a feature to toggle app to be live or down if we're undergoing maintenance | Rj | Sprint 24 | 2024-07-15 | 2024-07-12 | Medium
185 | Error - Modified 404, 503, 500 error pages | Rj | Sprint 24 | 2024-07-15 | 2024-07-12 | Medium
186 | Banner - Added a feature to create, edit and delete a banner to show on the app, can be used if we're undergoing system maintenance or showing announcements to every users. | Rj | Sprint 24 | 2024-07-15 | 2024-07-17 | Medium
187 | Cases - View Case Info and Documents | Rj | Sprint 24 | 2024-07-15 | 2024-08-12 | Medium
188 | Cases - Import data from a CSV | Rj | Sprint 24 | 2024-07-15 |  | Important
189 | Cases - Storage - Store files to a unique folder per case | Rj | Sprint 24 | 2024-07-15 | 2024-08-09 | Important
190 | Cases - Regular Case Proceeding - Change case statuses based on timeframe indicated | Rj | Sprint 24 | 2024-07-15 |  | Important
191 | Calendar Events - Each case can have multiple Mandatory Conference and Mediation Events | Rj | Sprint 24 | 2024-07-22 | 2024-08-08 | Medium
192 | Cases - Regular Case Proceeding - Proof of Mailing that can be tagged to multiple cases. | Rj | Sprint 24 | 2024-07-22 |  | Medium
193 | Old Cases - Old Cases Resource with CRUD | Rj | Sprint 24 | 2024-07-23 | 2024-07-30 | Important
194 | Old Cases - Old Case Files Upload and Viewing | Rj | Sprint 24 | 2024-07-23 | 2024-07-30 | Important
195 | Old Cases - Files uploaded should be stored in a folder named according to the case number | Rj | Sprint 25 | 2024-08-01 | 2024-08-09 | Important
196 | Old Cases - Files uploaded will be merged alphabetically into a single pdf document and be stored on merged_pdfs folder | Rj | Sprint 25 | 2024-08-01 | 2024-08-09 | Important
197 | Old Cases - Deleting an Old Case should also delete the directory of its uploaded files as well as the merged document | Rj | Sprint 25 | 2024-08-01 | 2024-08-09 | Medium
198 | Cases - Files uploaded should be stored in a folder named according to the case number | Rj | Sprint 25 | 2024-08-01 | 2024-08-09 | Important
199 | Cases - All the Files Uploaded should be merged alphabetically into a single pdf document and be stored on merged_pdfs folder. Each file upload related to it should be appended to the all_files column. | Rj | Sprint 25 | 2024-08-01 | 2024-08-09 | Important
120 | Cases - File Upload - Signed Summons file should be appended to the all_files and be able to be included on merged pdf file. | Rj | Sprint 25 | 2024-08-01 | 2024-08-09 | Important
121 | Cases - File Removal, Previous file of Signed Summons should also be deleted to the designated file folder of a particular case. | Rj | Sprint 25 | 2024-08-01 | 2024-08-09 | Important
122 | Old Cases - Merged Document Action Button to open a modal and preview the merged pdf file. | Rj | Sprint 25 | 2024-08-01 | 2024-08-09 | Medium
123 | Cases - Merged Document Action Button to open a modal and preview the merged pdf file. | Rj | Sprint 25 | 2024-08-01 | 2024-08-09 | Medium
124 | Security - 2FA feature before logging in. Email for 2FA code will be sent to the user's email and will have to input the code to the app to continue logging in | Rj | Sprint 25 | 2024-08-01 | 2024-08-07 | Important
125 | Cases - File Upload - POS - Summons file should be appended to the all_files and be able to be included on merged pdf file. | Rj | Sprint 25 | 2024-08-01 | 2024-08-09 | Important
126 | Cases - File Removal of POS -Summons - Delete the pdf files on the file folder if it is changed or deleted already | Rj | Sprint 25 | 2024-08-01 | 2024-08-09 | Important
127 | Users - Add a role for commissioner and they should be assigned to branches under them | Rj | Sprint 25 | 2024-08-01 | 2024-08-09 | Medium
128 | Cases - Notice of Mediation Teleconference pdf generation | Rj | Sprint 25 | 2024-08-05 | 2024-08-05 | Important
129 | Cases - Notice of Mediation Face to Face pdf generation | Rj | Sprint 25 | 2024-08-05 | 2024-08-05 | Important
130 | Cases - Add contact fields for counsels of complainants and representatives | Rj | Sprint 25 | 2024-08-05 | 2024-08-05 | Important
131 | Cases - File Upload - Answers and Other Pleadings files should be appended to the all_files and be able to be included on merged pdf file. | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
132 | Cases - File Removal of Answers and Other Pleadings files - Delete the pdf files on the file folder if it is changed or deleted already | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
133 | Cases - File Upload - Signed MCs should be appended to the all_files and be able to be included on merged pdf file. | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
134 | Cases - File Removal of Signed MCs - Delete the pdf files on the file folder if it is changed or deleted already | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
135 | Cases - File Upload - POS of MCs should be appended to the all_files and be able to be included on merged pdf file. | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
136 | Cases - File Removal of POS of MCs - Delete the pdf files on the file folder if it is changed or deleted already | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
137 | Cases - File Upload - Minutes for MC should be appended to the all_files and be able to be included on merged pdf file. | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
138 | Cases - File Removal of Minutes for MC - Delete the pdf files on the file folder if it is changed or deleted already | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
139 | Cases - File Upload - Notice for Mediation should be appended to the all_files and be able to be included on merged pdf file. | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
140 | Cases - File Removal of Minutes for MC - Delete the pdf files on the file folder if it is changed or deleted already | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
141 | Cases - File Upload - POS for Mediation should be appended to the all_files and be able to be included on merged pdf file. | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
142 | Cases - File Removal of POS for Mediation - Delete the pdf files on the file folder if it is changed or deleted already | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
143 | Cases - File Upload - Mediator's Reports should be appended to the all_files and be able to be included on merged pdf file. | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
144 | Cases - File Removal of Mediator's Reports - Delete the pdf files on the file folder if it is changed or deleted already | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
145 | Cases - File Upload - Motion for Approval of CA should be appended to the all_files and be able to be included on merged pdf file. | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
146 | Cases - File Removal of Motion for Approval of CA - Delete the pdf files on the file folder if it is changed or deleted already | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
147 | Cases - File Upload - Judgement upon Compromise file should be appended to the all_files and be able to be included on merged pdf file. | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
148 | Cases - File Removal of Judgement upon Compromise file - Delete the pdf files on the file folder if it is changed or deleted already | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
149 | Cases - File Upload - Signed Order of Finality file should be appended to the all_files and be able to be included on merged pdf file. | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
150 | Cases - File Removal of Signed Order of Finality file - Delete the pdf files on the file folder if it is changed or deleted already | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
151 | Cases - File Upload - Certificate of Finality file should be appended to the all_files and be able to be included on merged pdf file. | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
152 | Cases - File Removal of Certificate of Finality file - Delete the pdf files on the file folder if it is changed or deleted already | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
153 | Cases - File Upload - Signed Order for Position Paper file should be appended to the all_files and be able to be included on merged pdf file. | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
154 | Cases - File Removal of Signed Order for Position Paper file - Delete the pdf files on the file folder if it is changed or deleted already | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
155 | Cases - File Upload - POS - Order for Position Paper file should be appended to the all_files and be able to be included on merged pdf file. | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
156 | Cases - File Removal of POS - Order for Position Paper file - Delete the pdf files on the file folder if it is changed or deleted already | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
157 | Cases - File Upload - Position Paper files should be appended to the all_files and be able to be included on merged pdf file. | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
158 | Cases - File Removal of Position Paper files - Delete the pdf files on the file folder if it is changed or deleted already | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
159 | Cases - File Upload - Signed Order Ripe for Resolution file should be appended to the all_files and be able to be included on merged pdf file. | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
160 | Cases - File Removal of Signed Order Ripe for Resolution file - Delete the pdf files on the file folder if it is changed or deleted already | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
161 | Cases - File Upload POS - Order Ripe for Resolution files should be appended to the all_files and be able to be included on merged pdf file. | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
162 | Cases - File Removal of POS - Order Ripe for Resolution files - Delete the pdf files on the file folder if it is changed or deleted already | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
163 | Cases - File Upload - Signed Notice of Decision files should be appended to the all_files and be able to be included on merged pdf file. | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
164 | Cases - File Removal of Signed Notice of Decision files - Delete the pdf files on the file folder if it is changed or deleted already | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
165 | Cases - File Upload - Decision files should be appended to the all_files and be able to be included on merged pdf file. | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
166 | Cases - File Removal of Decision files - Delete the pdf files on the file folder if it is changed or deleted already | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
167 | Cases - File Upload - POS - NOD files should be appended to the all_files and be able to be included on merged pdf file. | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
168 | Cases - File Removal of POS - NOD files - Delete the pdf files on the file folder if it is changed or deleted already | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
169 | Cases - File Upload - Appeal Memorandum files should be appended to the all_files and be able to be included on merged pdf file. | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
170 | Cases - File Removal of Appeal Memorandum files - Delete the pdf files on the file folder if it is changed or deleted already | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
171 | Cases - File Upload - Signed Order to Elevate files should be appended to the all_files and be able to be included on merged pdf file. | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
172 | Cases - File Removal of Signed Order to Elevate files - Delete the pdf files on the file folder if it is changed or deleted already | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
173 | Cases - File Upload - Notice of Receipt of Records files should be appended to the all_files and be able to be included on merged pdf file. | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
174 | Cases - File Removal of Notice of Receipt of Records files - Delete the pdf files on the file folder if it is changed or deleted already | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
175 | Cases - File Upload - Order of Dismissal files should be appended to the all_files and be able to be included on merged pdf file. | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
176 | Cases - File Removal of Order of Dismissal files - Delete the pdf files on the file folder if it is changed or deleted already | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
177 | Cases - File Upload - POS Order of Dismissal files should be appended to the all_files and be able to be included on merged pdf file. | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
178 | Cases - File Removal of POS Order of Dismissal files - Delete the pdf files on the file folder if it is changed or deleted already | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
179 | Cases - File Upload - Other Orders files should be appended to the all_files and be able to be included on merged pdf file. | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
180 | Cases - File Removal of Other Orders files - Delete the pdf files on the file folder if it is changed or deleted already | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
181 | Cases - File Upload - Order of Default files should be appended to the all_files and be able to be included on merged pdf file. | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
182 | Cases - File Removal of Order of Default files - Delete the pdf files on the file folder if it is changed or deleted already | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
183 | Cases - File Upload - Motion for Default files should be appended to the all_files and be able to be included on merged pdf file. | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
184 | Cases - File Removal of Motion for Default files - Delete the pdf files on the file folder if it is changed or deleted already | Rj | Sprint 25 | 2024-08-05 | 2024-08-09 | Important
185 | Old Cases - Adjudicator and Mediator should be manually typed (some are resigned or deceased). | Rj | Sprint 25 | 2024-08-09 | 2024-08-09 | Medium
186 | Cases - Uploaded files shouldn't be deleted 5 days after it was uploaded. | Rj | Sprint 25 | 2024-08-12 | 2024-08-16 | Medium
187 | Server - Setup and config the app on production environment. Can be accessed on 172.16.90.18 | Rj | Sprint 25 | 2024-08-12 | 2024-08-12 | Important
188 | Server - Setup and config the app on test/staging environment. Can be accessed on 172.16.90.18:8080 | Rj | Sprint 25 | 2024-08-12 | 2024-08-12 | Important
189 | File Upload - Fixing the limit of file size for the uploads. - 100MB max | Rj | Sprint 25 | 2024-08-13 | 2024-08-13 | Important
190 | Old Cases - Add Appeal Number column and input. Nullable and be inputted manually. | Rj | Sprint 25 | 2024-08-14 | 2024-08-14 | Medium
191 | Settings - Add Departments table and resource (CRUD) to be used for the users on the Central Office. | Rj | Sprint 26 | 2024-08-19 | 2024-08-21 | Important
192 | Old Cases - Appeal Number field is only for the members under OECC thus, only those Old Cases that has an Appeal Number are the cases that can only be viewed by the users under OECC. (????) | Rj | Sprint 26 | 2024-08-19 | 2024-08-21 | Important
193 | Users - Added the feature that only users with is_active = true, can log in the web app. Is active toggle is already on the users table. | Rj | Sprint 26 | 2024-08-20 | 2024-08-20 | Medium
194 | Task Board - For Proof of Mailing tasks for Legal Assistants Before POS - For Mailing Upload Proof of Mailing | Rj | UAT | 2024-08-28 | 2024-09-20 | Important
195 | Cases - Proof of Mailing - Status: For Mailing, Actions: Generate List Of Mailing & Upload the Mailing List with bar code/stamp. | Rj | UAT | 2024-08-28 | 2024-09-20 | Important
196 | Bug Fix - Updating the initial documents of case resets the merged pdf. | Rj | UAT | 2024-09-09 | 2024-09-20 | Important
197 | Bug Fix - Visibility of regular actions depending on its current status and other factors | Rj | UAT | 2024-09-09 | 2024-09-13 | Important
198 | Cases - List of Mailing for Signed Summons - Generation and Upload | Rj | UAT | 2024-09-09 | 2024-09-20 | Medium
199 | Cases - List of Mailing for Signed Notice of Mandatory Conference - Generation and Upload | Rj | UAT | 2024-09-09 | 2024-09-20 | Medium
200 | Cases - List of Mailing for Signed Notice of Mediation - Generation and Upload | Rj | UAT | 2024-09-09 | 2024-09-20 | Medium
201 | Cases - List of Mailing for Order of Payment - Generation and Upload | Rj | UAT | 2024-09-12 | 2024-09-20 | Medium
202 | Cases - List of Mailing for Order to Implead - Generation and Upload | Rj | UAT | 2024-09-12 | 2024-09-20 | Medium
203 | Cases - List of Mailing for Order to Inhibit - Generation and Upload | Rj | UAT | 2024-09-12 | 2024-09-20 | Medium
204 | Cases - Generate and customize Mediator's Report. | Rj | UAT | 2024-09-12 | 2024-09-27 | Important
205 | Users - Fix edit; remove the password field so that the password of the user will not be updated - Joel | Joel | UAT | 2024-09-19 | 2024-09-27 | Medium
206 | Users - Fix the branch and department/division fields visibility - Joel | Joel | UAT | 2024-09-19 | 2024-09-27 | Medium
207 | Users - Fix the filter of the Legal Assistant field; so that only the users with legal assistant role will be displayed on the choices - Joel | Joel | UAT | 2024-09-19 | 2024-09-27 | Medium
208 | Users - Fix create/edit; Visibility of Legal Assistant Field. If the chosen role is Assistant Regional Adjudicator, it will be shown. Else, it will be hidden - Joel | Joel | UAT | 2024-09-19 | 2024-09-27 | Medium
209 | Cases - Fix phone input that it will only accept numbers starting 09, 9 or +63 - Joel | Joel | UAT | 2024-09-24 | 2024-09-27 | Medium
210 | Users - Add gender field - Joel | Joel | UAT | 2024-09-25 | 2024-09-27 | Medium
211 | Users - Add an optional prefix field - Joel | Joel | UAT | 2024-09-25 | 2024-09-27 | Medium
212 | Users - Add an optional suffix field - Joel | Joel | UAT | 2024-09-25 | 2024-09-27 | Medium
213 | Users - Customize request reset password and reset user's password forms - Rj | Rj | UAT | 2024-09-25 | 2024-09-27 | Medium
214 | Cases - Checkbox verification for each regular case actions before submitting - Joel | Joel | UAT | 2024-10-01 | 2024-10-11 | Important
215 | Cases - Fix regular case actions visibility; remove change or undo functionality for each action - Rj | Rj | UAT | 2024-10-01 | 2024-10-11 | Important
216 | Cases - Fix all the regular case action's forms; make them always required - Rj | Rj | UAT | 2024-10-02 | 2024-10-11 | Important
217 | Cases - For raffling cases tab; can only be seen by SuperAdmin and the Raffling Officer of the specific branch - Rj | Rj | UAT | 2024-10-08 | 2024-10-08 | Medium
218 | Branches - Add address line 1, address line 2, city/municipality and province fields and column - Rj | Rj | UAT | 2024-10-11 | 2024-10-11 | Medium
219 | Cases - Fix city/municipality and province displayed on generation of Summons pdf - Rj | Rj | UAT | 2024-10-11 | 2024-10-11 | Important
220 | Cases - Implement that only ONE user can update a case at the same time - Rj (to be tested) | Rj | UAT | 2024-10-11 | 2024-10-11 | Medium
221 | Cases - Implement Request and Allow request to edit the uploaded files of a particular case - Joel | Joel | UAT | 2024-10-14 |  | Important
222 | Revision for Create Case - Branch field should be auto selected - Rj | Rj | UAT | 2024-10-14 | 2024-10-14 | Low
223 | Revision for Create Case - Nature of cases field, should have others and specify - Joel | Joel | UAT | 2024-10-14 | 2024-10-14 | Low
224 | Revision for Create Case - Add functionality to enable/disable all the persons involved in the case - Rj | Rj | UAT | 2024-10-14 | 2024-10-14 | Important
225 | Revision for View Case - Only the Adjudicator/Legal Assistant and Legal Admin can view all the files - Rj | Rj | UAT | 2024-10-14 | 2024-10-14 | Important
226 | Revision for the Generation of Summons - Date may be inputted or left as blank - Rj | Rj | UAT | 2024-10-14 | 2024-10-15 | Low
227 | Revision of the Summons template | Rj | UAT | 2024-11-11 | 2024-11-20 | Important
228 | Revision for Generation of List of Mailing - Will have 3 options: Personal, Philpost and Private Courier (We need samples of each option) | Rj | UAT | 2024-10-15 | 2024-11-20 | Important
229 | Revision for Uploading of Summons - Add Date of Issuance - Rj | Rj | UAT | 2024-10-14 | 2024-10-15 | Medium
230 | Additional for Create Case - Add contact details for representatives - Rj | Rj | UAT | 2024-10-14 | 2024-10-14 | Low
231 | Additional for uploading Signed Summons - Date of Issuance input - Rj | Rj | UAT | 2024-10-15 | 2024-10-15 | Important
231 | Revision for POS - Summons - Add complainant - Rj | Rj | UAT | 2024-10-15 | 2024-10-22 | Important
232 | Cases - Consolidation of Case |  | UAT | 2024-10-15 |  | Important
233 | Revision of Case Flow - Mediation will be the next process after Summons (TBD) |  | UAT | 2024-10-15 |  | Important
234 | Cases - Case may "reset", but it will retain the flow of the previous proceedings (Remand) - Pending |  | UAT | 2024-10-15 |  | Important
235 | Cases - Order to Comment, Order to File Computerized Complaint, Order to Submit Accurate Address - Pending |  | UAT | 2024-10-15 |  | Important
236 | Cases - Summary of Proceedings - Pending |  | UAT | 2024-10-15 |  | Important
237 | Cases - Entry of Judgement - Pending |  | UAT | 2024-10-15 |  | Important
238 | Cases - Generation of Mediator's Report - Select (multiple) Input for Complainant/Respondent/Counsel - Joel | Joel | UAT | 2024-10-15 | 2024-10-18 | Important
239 | Cases - Bug fix on Answers Action - Doesn't update the uploaded_at and uploaded_by fields upon changing of the file - Rj | Rj | UAT | 2024-10-16 | 2024-10-16 | Medium
240 | Cases - Add Proof of Service Action, wherein all the POS can be uploaded on a single page by selecting the POS Type (to be tested, waiting for new statuses (removing the Awaiting POS statuses)) - Rj | Rj | UAT | 2024-10-16 | 2024-12-06 | Important
241 | Cases - List of Mailing (Certificate of Service) pdf template (HTML/CSS) - Rj | Rj | UAT | 2024-10-28 | 2024-12-06 | Important
242 | Cases - List of Mailing (Certificate of Service) input form to be filled for generation - Rj | Rj | UAT | 2024-10-31 | 2024-12-06 | Important
243 | Users - Add "Process Server" Role
244 | Cases - Complainant/Respondent may be an individual/corporation or a group. If it is a group, it should be capable to add members to it. (to be used for generating docs) | Rj | UAT | 2024-11-11 | 2024-12-06 | Important
245 | Cases - Added a Complainant/Respondent Counsel fields. They can be also be an individual or as a Legal Group. If it is a Legal Group, members(attorneys) can be added to them. (to be used for generating docs) | Rj | UAT | 2024-11-11 | 2024-12-06 | Important
246 | Login - Make the login form compressed (on mobile) | Joel | UAT | 2024-11-19 | 2024-11-20 | Low
247 | View Case - Modify the complainant and respondent table due to the change of data stored (From Requirement # 244 and #245) | Rj | UAT | 2024-11-20 | 2024-12-06 | Medium
248 | Edit Request - Roles & Permission (Limit Access to Approval Button for specific Roles) | Joel | UAT | 2024-11-20 | 2024-11-20 | Medium
249 | Cases - Add a functionality of bulk raffling of adjudicator for Regular Cases | Rj | UAT | 2024-11-25 | 2024-11-26 | Medium
250 | Cases - Add a functionality of bulk raffling of mediator for Regular Cases | Rj | UAT | 2024-11-25 | 2024-11-26 | Medium
251 | Cases - Add a functionality to generate Result of Raffling for HOA and REM cases | Rj | UAT | 2024-11-26 | 2024-12-06 | Important
252 | Cases - Other Motions; motions that needs to be resolved by the adjudicator before having a Decision - Pending |  | UAT | 2024-11-27 |  | Important
253 | Cases - Generation of Notice of Mediation Conference for Online Conference | Joel | UAT | 2024-11-28 | 2024-11-29 | Important
254 | Cases - Generation of Notice of Mediation Conference for Face to Face | Joel | UAT | 2024-11-28 | 2024-11-29 | Important
255 | Users - Adding the Suffix and Prefix in Full name | Joel | UAT | 2024-11-29 | 2024-11-29 | Low
256 | Cases - Add a toggle button for Legal assistant for authority of the adjudicator in the Notice of MC | Joel | UAT | 2024-12-02 | 2024-12-03 | Medium
257 | Cases - Generation of Notice of Mandatory Conference for Online Conference | Joel | UAT | 2024-12-02 | 2024-12-03 | Important
258 | Cases - Generation of Notice of Mandatory Conference for Face to Face | Joel | UAT | 2024-12-02 | 2024-12-03 | Important
259 | Cases - Generation of Order for Position Paper | Joel | UAT | 2024-12-03 | 2024-12-05 | Important
260 | Cases - Update the PDFcontroller for the Generated files | Joel | UAT | 2024-12-05 | 2024-12-16 | Important
261 | Files - Upon uploading the file, it needs to have a random string for it to have a unique identifier to not overwrite same file name (If user chose a file with the same file name that is already existing on its storage/folder) | Joel | UAT | 2024-12-09 | 2024-12-16 | Important
262 | Case - Generation of Order for Resolution (content depends on the complainant & respondent; if they already submitted each of their Position Paper or not) | Rj | UAT | 2024-12-09 | 2025-01-07 | Important
263 | Notifications - System Notif for raffling (must be raffled within 8 days from the receipt of complaint/date created) - For Raffling Officer/Legal Admin - alert on due date - Testing | Rj | UAT | 2024-12-09 |  | Important
264 | Notifications - Email Notif for raffling (must be raffled within 8 days from the receipt of complaint/date created) - For CRA/Legal Admin - alert a day before |  | UAT | 2024-12-09 |  | Important
265 | Notifications - System Notif for Issuance of Summons must be 10 calendar days from the date assigned to adjudicator - For Legal Assistant/Adjudicator - alert on due date - Testing | Rj | UAT | 2024-12-09 |  | Important
266 | Notifications - Email Notif for Issuance of Summons must be 10 calendar days from the date assigned to adjudicator - For CRA/Legal Admin/Legal Assistant/Adjudicator - alert a day before |  | UAT | 2024-12-09 |  | Important
267 | Notifications - System Notif for Answers - must have an Answer 20 calendar days from receipt of Proof of Service of Summons / 60 days from issuance of summons (If there's still no Proof of Service of Summons) - Adjudicator/Legal Assistant - alert on due date - Testing | Rj | UAT | 2024-12-09 |  | Important
268 | Notifications - Email Notif for Answers - must have an Answer 20 calendar days from receipt of Proof of Service of Summons / 60 days from issuance of summons (If there's still no Proof of Service of Summons) - Adjudicator/Legal Assistant - alert a day before |  | UAT | 2024-12-09 |  | Important
269 | Notifications - System Notif for Issuance of Notice for Mandatory Conference - must issue 5 days from the date of receipt of last Answer - For Adjudicator/Legal Assistant - alert on due date - Testing | Rj | UAT | 2024-12-09 |  | Important
270 | Notifications - Email Notif for Issuance of Notice for Mandatory Conference - must issue 5 days from the date of receipt of last Answer - For CRA/Legal Admin/Adjudicator/Legal Assistant - alert a day before |  | UAT | 2024-12-09 |  | Important
271 | Notifications - System Notif for Allowable time to have conference/mediation - 60 days from the 1st Mandatory Conference/Hearing - Legal Assistant/Adjudicator - alert on due date - Testing | Rj | UAT | 2024-12-09 |  | Important
272 | Notifications - Email Notif for Allowable time to have conference/mediation - 60 days from the 1st Mandatory Conference/Hearing |  | UAT | 2024-12-09 |  | Important
273 | Notifications - System Notif for submission of Position Paper - 15 days from the latest POS / 30 days from issuance of Order for Position Paper - Legal Assistant/Adjudicator - alert on due date - Testing | Rj | UAT | 2024-12-09 |  | Important
274 | Notifications - Email Notif for submission of Position Paper - 15 days from the termination of Mandatory Conference |  | UAT | 2024-12-09 |  | Important
275 | Notifications - System Notif for Decision - Needs to have a Decision issued within 90 days from the date that an Order for Resolution has been issued - Legal Assistant/Adjudicator - alert on due date - Testing | Rj | UAT | 2024-12-09 |  | Important
276 | Notifications - Email Notif for Decision - Needs to have a Decision issued within 90 days from the date that an Order for Resolution has been issued |  | UAT | 2024-12-09 |  | Important
278 | Case - Before creating the case, it should have a cofirmation checkbox that the data inputted are correct and a view/pdf for checking the inputted data upon creation for verification | Joel | UAT | 2024-12-10 | 2024-12-16 | Important
279 | Case - Minutes of Mandatory Conference should have the datetime of hearing | Rj | UAT | 2024-12-11 | 2024-12-16 | Medium
280 | Case - Report of Mediation should have the datetime of hearing |  | UAT | 2024-12-11 |  | Medium
281 | Settings - Holidays - Add Holiday resource with CRUD. The list can be updated by the super admins yearly, it can be updated through HolidaySeeder or manually through settings. (Added because of countdown timer where the period/time frame can be extended if the duedate is a holiday) | Rj | UAT | 2024-12-11 | 2024-12-16 | Medium
282 | Case - Countdown for raffling of regular case on cases table | Rj | UAT | 2024-12-16 | 2025-01-03 | Medium
282 | Case - Countdown for issuance of summons for regular case on cases table | Rj | UAT | 2024-12-16 | 2025-01-03 | Medium
283 | Case - Countdown for issuance of notice of mandatory conference on cases table | Rj | UAT | 2024-12-16 | 2025-01-03 | Medium
284 | Case - Countdown for allowable time of conference (60 days) on cases table | Rj | UAT | 2024-12-16 | 2025-01-03 | Medium
285 | Case - Countdown for submission of position paper on cases table | Rj | UAT | 2024-12-16 | 2025-01-03 | Medium
286 | Case - Countdown for issuance of decision within 90 days on cases table | Rj | UAT | 2024-12-16 | 2025-01-03 | Medium
287 | Code - Enhance and optimize functions and queries for better performance of the web app (Lessen the queries and cached some) | Rj / Joel | UAT | 2024-12-19 | 2025-01-13 | Important
288 | Case - Countdown Authorized Permission for Adjudicator,Legal Assist. and Mediator | Joel | UAT | 2025-01-07 | 2025-01-08 | Medium
289 | Case - Countdown Authorized Permission for CRA | Joel | UAT | 2025-01-07 | 2025-01-09 | Medium
290 | Case - Countdown Authorized Permission for Raffling Officer & Legal Admin | Joel | UAT | 2025-01-07 | 2025-01-09 | Medium
291 | Hash IDs for all models for security - URL doesn't display the exact id and is now hashed | Rj | UAT | 2025-01-10 | 2025-01-10 | Medium
292 | Calendar Events - Events for Mandatory and Mediation Conferences fixed | Rj | UAT | 2025-01-10 | 2025-01-10 | Low
293 | Server - Switch from using Laragon to NGINX standalone (For testing, if it will give occasional Bad Gateway 502 again) | Rj | UAT | 2025-01-14 | 2025-01-14 | Important
294 | Case - Other Pleadings of Litigants Action - (onhold, waiting for the list of motions and manifestations) | Rj | UAT |  |  | Important
295 | Case - Other Orders of Adjduicator - (onhold, waiting for the list of orders - the case is not under evaluation) | Rj | UAT |  |  | Important
296 | Case - Revision of uploading and storing of data of Official Receipts | Rj | UAT | 2025-01-17 | 2025-01-20 | Medium
297 | Case - Fix the rendering in generated document/s if the litigants has the same representative (To be tested) | Rj | UAT | 2025-01-23 |  | Important
298 | Case - Raffle the case to the Legal Assistants of the specific RAB. Will be assigned by the adjudicator of the case. | Joel | UAT | 2025-01-21 | 2025-01-24 | Important
299 | Case - Multiple emails of litigants and counsels (ONHOLD)
300 | Case - Other Orders of Adjudicator (if the case is under evaluation) - add Order of Compliance (will remake the whole action for this; includes Order of Payment, Order to Implead, Order to Inhibit) | Rj | UAT | 2025-01-27 |  | Important
301 | E-Docket - To arrange the files in order and then merge them based on the list (functionality) | Rj | UAT | 2025-01-22 | 2025-01-24 | Low
302 | E-Docket - UI of the listing of files (design) | Joel | UAT | 2025-01-27 | 2025-01-30 | Low
303 | Services - Configuring the bugs and error in Nginx | Joel | UAT | 2025-01-24 | 2025-01-24 | Important
304 | Case - Assigning of Legal Assistants Authentication for every role | Joel | UAT | 2025-01-24 | 2025-01-27 | Important
305 | Case - Setting up the Assigning of Legal Assistant for every branch | Joel | UAT | 2025-01-24 | 2025-01-27 | Low
306 | Case - Update the Create Existing Case with initial uploading file random STR.. | Joel | UAT | 2025-01-27 | 2025-01-28 | Low
307 | Case - Update the Uploading of initial files in to Copy of Main Files | Joel | UAT | 2025-01-30 | 2025-01-31 | Low
308 | Case - Farm out cases to other branches (For testing) | Rj | UAT | 2025-02-03 | 2025-02-04 | Medium
309 | Case - Generation and upload of Transmittal Letter (waiting for template) | Rj | UAT | 2025-02-04 |  | Medium
310 | Case - Revision of Order for Default process | Rj | UAT | 2025-02-11 | 2025-02-13 | Medium
311 | Case - added Resolve Motions action (ongoing; waiting for OTHER MOTIONS that can be resolved as each may have different processes) | Rj | UAT | 2025-02-11 |  | Important
312 | Storage - Fixed storing of files for cases created | Rj | UAT | 2025-02-12 | 2025-02-13 | Important
313 | Case - Period can now be viewed by Commissioner role | Rj | UAT | 2025-02-12 | 2025-02-14 | Low
314 | Case - On generating Notice for MC, if the respondent is "in default", put them in copy furnished section of the document | Joel | UAT | 2025-02-13 |  | Medium
315 | Case - On creating case, removed SPA upload for representatives; as the file can be included in "Annexes" by the complainant/s. SPA will be uploaded now on main files form | Rj | UAT | 2025-02-12 | 2025-02-14 | Low
316 | Case - System notification to the adjudicator assigned | Rj | UAT | 2025-02-11 | 2025-02-13 | Low
317 | Case - System notification to the mediator assigned | Rj | UAT | 2025-02-11 | 2025-02-13 | Low
318 | Case - Auto fill of contact details of RAB in generating documents | Joel | UAT | 2025-02-13 | 2025-02-14 | Low
319 | Appeals - Database structure for appeals | Rj | UAT | 2025-02-04 | 2025-02-10 | Important
320 | Appeals - CRUD for Appeals | Rj | UAT | 2025-02-04 | 2025-02-10 | Important
321 | Appeals - Table design | Rj | UAT | 2025-02-04 | 2025-02-10 | Important
322 | Appeals - View page for specific appeal case | Rj | UAT | 2025-02-04 | 2025-02-10 | Medium
323 | Case - Position Paper Single File to Multiple uuid and Single file for Individidual uuid | Joel / Rj | UAT | 2025-02-07 | 2025-02-11 | Important
323 | Case - Answers Single File to Multiple uuid and Single file for Individidual uuid | Joel / Rj | UAT | 2025-02-13 | 2025-02-14 | Important
324 | Case - Answers due date Adjusment | Joel | UAT | 2025-02-13 | 2025-02-14 | Important
325 | Case - Position Paper Code and storing structure modified | Joel | UAT | 2025-02-07 | 2025-02-11 | Medium
326 | Case - Answers Code and storing structure modified | Joel | UAT | 2025-02-13 | 2025-02-14 | Medium
327 | Case - Adding HintIcon for clarification for all forms | Joel | UAT | 2025-02-07 | 2025-02-10 | Low
328 | Case - Fix Bugs in Double generation of Respondents | Joel | UAT | 2025-02-07 | 2025-02-10 | Low
329 | Case - Adding Options for Font Size and Layout (Margin) | Joel | UAT | 2025-02-07 | 2025-02-10 | Low
330 | Case - CMS Comments (NCR) | Joel | UAT | 2025-02-07 | 2025-02-14 | Important
331 | Case - Generation of Order for Resolution be optional | Rj | UAT | 2025-02-07 | 2025-02-10 | Low
332 | Case - Spacing of all documents generated spacing | Joel | UAT | 2025-02-07 | 2025-02-10 | Low
333 | Dashboard - Make widgets clickable then redirect it to its corresponding table view with auto filter depends on the branch of the widget that was clicked (testing) | Rj | UAT | 2025-02-18 | 2025-02-19 | Low
334 | Dashboard - Make the rows of table widget clickable then redirect user to its corresponding view page (testing) | Rj | UAT | 2025-02-18 | 2025-02-19 | Low
| Case - POS Summons Service Status: (Succesful or failed) | Joel | UAT | 2025-02-17 | 2025-02-19 | Important
| Case - Remodified blade structure of list of mailing for filtering Summons POS | Joel | UAT | 2025-02-19 | 2025-02-21 | Important
| Case - Track Result of attempt | Joel | UAT | 2025-02-21 |  | Important

## HRMIS
Requirements Traceability Matrix
Project | Pediatric Blood Center Mobile Blood Donation System
As of | 2025-04-08
Responsible | Mark Oliver Roman
Requirement # | Description | Sprint Reference | Date Start | Date Completed | Priority | Test Case Reference | Date Start | Date Completed | Status | Requestor | User Acceptance Validation | Remarks
1 | Prototypes / Wireframe - Landing Page (Change Button label from "Blood Drive Hosting" to "Blood Drive Schedule") | Sprint 1 | 2025-04-07
2 | Prototypes / Wireframe - Landing Page (Change Dropdown option label from "Apply to Host a Blood Drive" to "Agency Registration") | Sprint 1 | 2025-04-07
3 | Prototypes / Wireframe - Landing Page (Change Dropdown option label from "Blood Program Leader Login" to "Agency - Account Manager / Coordinator Login") | Sprint 1 | 2025-04-07
4 | Prototypes / Wireframe - All Forms: Address fields: Add Municipality, Region; Country: Default to "Philippines" | Sprint 1 | 2025-04-07
5 | Prototypes / Wireframe - All Forms: Change form fields (Change label from gender to sex) | Sprint 1 | 2025-04-07
6 | Prototypes / Wireframe - All Forms: Address fields: Pre-populated address options. | Sprint 1 | 2025-04-07
7 | Prototypes / Wireframe - Donor Information: Change field label and options (Label: "Regular Donor?" ¦ Options: (Yes / No)) | Sprint 1 | 2025-04-07
8 | Prototypes / Wireframe - Donor Information: Add form fields (Label: "Last Donation Date" ¦ Options: (Yes / No) & Label: "Blood Service Facility/Hospital/Location"). | Sprint 1 | 2025-04-07
9 | Prototypes / Wireframe - Donor Information: Change form fields (Upload a government-issued ID instead of a donor ID.) | Sprint 1 | 2025-04-07
10 | Prototypes / Wireframe - Donor Information: Remove Medical History field and file uploads. | Sprint 1 | 2025-04-07
11 | Prototypes / Wireframe - Donor Information: Restriction: Middle Name (Restrict middle initial inputs) | Sprint 1 | 2025-04-07
12 | Prototypes / Wireframe - MBDT Appointment Management: Reason for deferral (predefined dropdown options c/o mbdt). | Sprint 1 | 2025-04-07
13 | Prototypes / Wireframe - MBDT Appointment Management: Add Field - Remarks (for the Reason for deferral) | Sprint 1 | 2025-04-07
14 | Prototypes / Wireframe - Donor Card ID: Change label (Use "pos" or "neg" instead of a "+" ior "-" for rh factor) | Sprint 1 | 2025-04-07
15 | Feature: Allow data imports for the past donation events. Data fields to import c/o MBDT (MBDT Module) | Sprint 2D | 2025-04-28
16 | Feature: Report Generation (User defined c/o MBDT) | Sprint 2D | 2025-04-28
17 | Feature: Event Calendar (Color Coding for Booked Appointments) (Agency Module) | Sprint 2B | 2025-04-14
18 | Feature: Feedback/Service Evaluation (Donors Module) | Sprint 2C | 2025-04-21
19 | FAQ's / Chatbot (CMS Module) | Sprint 2E | 2025-05-12

## Ref
Status (Support) | Type | Level | Threat Source | Priority | Consequence | Risk Rating | Forwarded | Support (Plan) | Level of Escalation | Action | Evaluation Rating
None | None | None | None | None | None | None | None | None | None | None | None
Waiting | Server | Almost Certain | 1-Loss of essential services | Urgent | Catastrophic | Very High | Yes | Open | Level 1 | Avoid | Needs Improvement
Not Resolved | Network | Likely | 2-Fire, smoke | Important | Major | High | No | Closed | Level 2 | Reduce | Adequate
Resolved | Telephony | Possible | 3-Natural disasters | Medium | Moderate | Tolerable |  |  | Level 3 | Share | Strong
On Hold | Software/System | Unlikely | 4-Terrorist attack | Low | Minor | Low |  |  | Level 4 | Transfer | Effective
| Hardware | Rare | 5-Malicious action |  | Insignificant | Very Low |  |  |  | Accept
| Others |  | 6-Errors and negligence
7-Loss of key staff
8-Industrial action
9-Power failure
10-Telecommunication failure
11-Malicious software
12-Insiders misuse IT
13-IT System crash
14-IT System failure
15-Website development carelessness
16- Obsolete Hardware/Software
17-Attack from hacker, cracker, computer criminal